## Table 1
Rehab/Construction Budget
Property Address:
Instructions: Complete the yellow column only for your loan application. - We will use the Draw columns for future Draw Requests.
Draw Requests
Line Items | Description of item, labor, material, brands, etc… | Estimated Cost/Budget | Draw 1- Requested 1/2/2018 | Draw 2- Requested 2/2/2018 | Draw 3- Requested 3/15/2018 | Draw+ | % Complete | Status | Notes & Uploads
Interior
Demolition |  | 1000 | 1000 |  |  |  | 100% | Finished | All work looks 100% complete. See attached pics.
Paint |  | 5000 |  |  | 4500 |  | 90% | Not Started
Flooring | doing 5000 sq ft total- 2500 marble & 2500 wood | 40000 |  | 20000 | 20000 |  |  | In Progress
Doors |  | 1800 |  |  | 1800 |  |  | Pending Inspection
HVAC |  | 5000 | 5000
Eletrical-Rough |  | 3500 | 3500 |  |  |  |  | Finished
Eletrical-Finish/Fixtures |  | 2500 |  |  | 2500
Plumbing-Rough |  | 2500 | 2500
Plumbing-Finish/Fixtures |  | 2500 |  | 2500
Water Heater |  | 500 |  | 500
Cabinets-Kitchen |  | 12000 |  | 8500
Cabinets-Bath |  | 1500 |  | 1500
Counters-Kitchen |  | 4000 |  | 4000
Counters-Bath |  | 1200 |  | 1200
Appliances |  | 5000 |  |  | 4500
Framing/ Drywall |  | 2500
Trim/Mouldings/Baseboard |  | 600
Closets |  | 6000
Stairs
Audio/Visual |  | 2000 | 2000
Custom Work
Other+
EXTERIOR
New Addition/Shell
Exterior Paint |  | 4000 |  |  | 4000
Stucco |  | 1500 | 1500
Windows
Doors |  | 1000 |  | 1000
Siding/Trim
Roof |  | 2500 | 2500
Landscape & Fencing |  | 2000 |  |  | 2000
Garage
Decks & Patios
Driveway/Walkway
Pool/Waterscape |  | 25000 | 24000
Irrigation
Well/Septic
Other+
GENERAL
Architect Fees |  | 3000 | 3000
Engineer Fees
Permit Fees |  | 1800 | 500 | 500
Site Setup
Survey |  | 450 | 450
Dumspters |  | 1500 |  | 700
Mold/termite Remediation
Staging
Foundation
Structural
Cost Overun Reserve |  | 10000
Other+
Status on Draw |  |  | Draw Disbursed | Pending Inspection
Total |  | 151850 | 45950 | 40400 | 39300
Current Escrow Balance |  | 26200
Overall % Complete |  | -82.7461
Total Draws |  | 125650
Initial Loan Amount Funded |  | 400000
Total Current Balance |  | 525650
Note on D5: Chris Fuelling: A borrower will be able to request a draw here and fill in values for eachline item that was completed.
Note on I5: Chris Fuelling: Add values: Not Started, 25% Complete, 50% Complete, 75% Compete, Finished, In Progress, Pending Inspection, Needs Budget Approval, Canceled, This page/module for draw management will be accessible to a 3rd party contact like a home inspector... We do NOT want borrowers to ever be able to edit the status of a line item
Note on J5: Chris Fuelling: The home inspector or any back office user can create notes & upload pics/files.
Note on A7: Chris Fuelling: This is a category header/label
Note on A8: Chris Fuelling: All these items will be the default line items. However, All users can remove line items and add new items when required. Is it possible to have a master rehab budget, controlled on the PC profile level, which becomes the company default?
Note on D8: Chris Fuelling: The value entered can never exceed the budgeted amount.
Note on H9: Chris Fuelling: Calculate % complete using total draws over total budget amount. If 100% complete, change color to light grey.
Note on B10: Chris Fuelling: Allow uploads of .doc, .xls, pics or pdfs etc.. . Track which user made notes and which user made uploads. Can we support muti-thread comments/notes for various users?
Note on D61: Chris Fuelling: These status drp downs are for back office only. Use these values: Pending Review [default status after a draw request is created] Needs Manager Approval/Override Draw Disbursed Draw Denied Pending Re-Inspection
Note on C62: Chris Fuelling: This is total rehab budget
Note on D62: Chris Fuelling: this is total amount of each draw request fr each line item.
Note on C64: Chris Fuelling: This is Total Budget - [all approved/disbursed draws]
Note on C65: Chris Fuelling: Calculate based off of Current Escorw balance over the total rehab budget.
Note on C68: Chris Fuelling: Add up total draws disbursed.
Note on C69: Chris Fuelling: Pulled from loan into tab